## Sheet1
Task # | Task Name | Duration | Start Date | Finish Date | Dependency | Resource | Outline Level
1 | Soccer camp application Web page available | 0d | 2002-01-04 08:00 |  |  |  | 1
2 | Application deadline | 0d | 2002-02-04 08:00 |  |  |  | 1
3 | Acceptance notification | 0d | 2002-02-18 08:00 |  |  |  | 1
4 | Payment due | 0d | 2002-03-18 08:00 |  |  |  | 1
5 | Pre-camp conditioning | 45d | 2002-02-04 08:00 |  | 2 |  | 1
6 | Soccer camp begins | 0d | 2002-04-08 08:00 |  | 5 |  | 1
7 | Orientation | 0d | 2002-04-08 08:00 |  |  |  | 1
8 | Conditioning and basic skills | 4d | 2002-04-09 08:00 |  |  |  | 1
9 | Advanced skills and game strategy | 5d | 2002-04-15 08:00 |  |  |  | 1
10 | The Big Game | 0d | 2002-04-22 08:00 |  |  |  | 1
11 | Soccer camp ends | 0d | 2002-04-22 08:00 |  |  |  | 1